## Sheet1
Development Timeline: Maze Game
Team 3: Team Blue Monday
| Development Start: |  | 2020-01-20
| Display Days: |  | 2 |  |  |  |  | 2020-01-31 | [23 empty] | 2020-02-01
[8 empty] | AM | [11 empty] | PM | [11 empty] | AM | [11 empty] | PM
TASK | ASSIGNED TO | PROGRESS | START | END | Estimated time | Remarks | Time | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Development
Feature 1: Display Menu | Marcus, Tee Kiat, Jun Wu | 100% | 2020-01-31 | 2020-01-31 | 4 hour
Feature 2: Read and load maze from file | Marcus | 100% | 2020-01-31 | 2020-01-31 | 2.5 hour
Feature 3: View Maze | Tee Kiat | 100% | 2020-01-31 | 2020-01-31 | 3 hour
Feature 4: Play maze game | Jun Wu | 100% | 2020-01-31 | 2020-02-01 | 5 hour | actual estimated time taken: 7 hour | bar: 5 to 6; 9 to AM 2
Feature 5: Configure Maze | Kevin | 100% | 2020-01-31 | 2020-02-01 | 5 hour | actual estimated time taken: 10 hour | bar: 5 to 6; 9 to AM 5
Legend | Unit Test
Development
Refactoring
Remarks:
Feature 4 and Feature 5 is not able to complete in time, due to QA hitting a major issue.
actual completion time had been added.
Legend | Unit Test
Development
Refactoring